## Execution403
Deliverable | 2022-10-14 | 2022-10-21 | 2022-10-28 | 2022-11-04 | 2022-11-11 | 2022-11-18 | 2022-11-22 | 2022-12-02
Buck Boost Converter Simulations | 2022-11-22: Not Started
ADC Code Written and Tested | 2022-11-22: In Progress
Database Setup and Testing | 2022-11-22: Completed
Selection of Passive Components | 2022-11-22: Behind Schedule
Ordering Passive Components | bar: 2022-10-21 to 2022-10-28
CSA Code Written and Tested | bar: 2022-10-21
ADC/CSA/Switch Test Circuit Integration | bar: 2022-10-21 to 2022-11-11
GUI Designed and Implemented | bar: 2022-10-28 to 2022-11-11
PCB Design | bar: 2022-10-28 to 2022-11-22
Motor Driver Code Written and Tested | bar: 2022-11-04 to 2022-11-11
System Animations | bar: 2022-11-11 to 2022-11-22
Testing Battery Charging | bar: 2022-10-28 to 2022-11-04
Testing Load Power Delivery | bar: 2022-11-04 to 2022-11-11
Testing GUI and Database Communication | bar: 2022-11-11 to 2022-11-22
Solar Power Generation Validation | bar: 2022-11-18 to 2022-11-22
Electrical I/O Validation | bar: 2022-11-18 to 2022-11-22
GUI and Database Validation | bar: 2022-11-18 to 2022-11-22
PCB Design Review | bar: 2022-11-22 to 2022-12-02
Demo | bar: 2022-12-02

## Execution404
Deliverable | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24
Status Update 1 | 2023-04-10: Not Started
PCB Ordered | 2023-04-10: In Progress
Touchscreen Integration | 2023-04-10: Completed
Power Supply Ordered | 2023-04-10: Behind Schedule
3D Printing Chassis | bar: 2023-01-23 to 2023-01-30
Solar Panel Rotation Algorithm Write | bar: 2023-01-23 to 2023-01-30
GUI Animation and Feature Updates | bar: 2023-01-30 to 2023-02-06
Status Update 2 | bar: 2023-02-13
PCB Soldering and Testing | bar: 2023-02-06 to 2023-02-13
Solar Panel Rotation Algorithm Testing | bar: 2023-02-06 to 2023-02-13
Power Supply Integration | bar: 2023-02-13 to 2023-02-20
Measurement I/O to GUI Testing | bar: 2023-02-06 to 2023-02-20
Status Update 3 | bar: 2023-02-27
PCB Revision and Testing | bar: 2023-02-20 to 2023-02-27
System Charge Integration Testing | bar: 2023-02-27 to 2023-03-06
Status Update 4 | bar: 2023-03-20
System Discharge Integration Testing | bar: 2023-03-06 to 2023-03-13
Status Update 5 | bar: 2023-04-03
System Validation | bar: 2023-03-13 to 2023-03-27
Final Update | bar: 2023-04-17
System Validation | bar: 2023-03-27 to 2023-04-17
Final Demonstration | bar: 2023-04-24

## Validation
References | Test Name | Success Criteria | Methodology | Status | Responsibility
3.2.1.1 | Maximum Battery Charge Time | The time to charge the battery shall be no longer than 12 hours. | The battery will be charged by the panel through the charge controller and while timed. | Untested | George Thuita
3.2.1.2 | Minimum Battery Discharge Charge | The time to discharge the battery shall be no shorter than 2 hours. | The battery will be discharged through the buck-boost converter and the time to discharge will be timed. | Untested | George Thuita
3.2.1.7 | Minimum Full Battery Capacity Charge | The battery should be charged to 900mAh. | The battery will be discharged across a known load and timed while tracking voltage to find the battery capacity. | Untested | George Thuita
3.2.3.1.4 | Buck Boost Converter Input Voltage Range | The input voltage range of the buck-boost converter should be between 2.5V and 3.7V. | A power supply set to the desired edge case voltages will be provided to the converter and the output shall remain constant. | Untested | George Thuita
3.2.3.2.4 | Peak Solar Panel Output Voltage | Peak output voltage of the solar panel should be 5.5V. | Voltage measurement will be taken at the panel leads when connected to charge controller and battery while exposed to sunlight. | Untested | George Thuita
3.2.3.2.5 | Charge Controller Output Voltage | Output voltage of the charge controller should be 3.7V to charge the battery. | Voltage measurement will be taken at the battery leads when connected to charge controller during operation. | Untested | George Thuita
3.2.3.2.6 | Buck Boost Converter Output Voltage Range | The output voltage of the buck-boost converter should be 3.7V with the specified input voltage range. | While the input voltage range is begin tested, the output voltage will also be measured to verify the output level. | Untested | George Thuita
3.2.1.5 | Minimum Motor Step Size | The minimum step size of the stepper motor across range of motion shall be no larger than 10 steps (18°) | The minimum step size of the motor will be excited and using a thin protrusion from the axis, the angular displacement will be measured. | Untested | Leo Predanic
3.2.1.12 | Maximum Switch Response Time | The maximum time to switch the PFET transistor shall take no longer than 2 seconds. | The voltage across the gate-source will be switched across a GPIO pin and the time to switch output voltages will be time averaged. | Untested | Leo Predanic
3.2.1.13 | Maximum ADC Response Time | The maximum time to sample an ADC channel shall take no longer than 2 seconds. | The ADC will have several measurement taken and the time average of the measurements will be used to determine sample time. | Untested | Leo Predanic
3.2.1.14 | Maximum Motor Response Time | The motor shall take no longer than 2 seconds to adjust when the control input is switched. | The motor input will switch and the time average of the motor response will be recorded to determine response time. | Untested | Leo Predanic
3.2.1.15 | Maximum Current Sense Amplifier Response Time | The current sense amplifier shall stabilize its output in no less than 2 seconds. | The CSA will be excited with several voltage pulses and the average time to stability will be measured. | Untested | Leo Predanic | Passed
3.2.1.16 | ADC Sample Voltage Accuracy | The ADC sampled voltage will be 90% or greater in accuracy (less than 10% error is tolerated). | Many voltage values from ground to reference at the ADC channels will be provided and the displayed voltage will be compared to the actual. | Untested | Leo Predanic
3.2.3.1.2 | MCU Input Voltage and Current Level | The input voltage/current level for Raspberry Pi MCU shall be 5V 3A DC from 100-240V 50-60Hz AC outlet . | The voltage and current draw will be measured using a multimeter. | Untested | Leo Predanic
3.2.1.8 | Functional User Interaction System Response | GUI must be able to display or respond to acknowledge user interaction. | User will interact with system prompts and display while GUI prints out acknowledgement that interaction was processed. Used in integration. | Untested | Brandon Cenci
3.2.1.9 | Functional User Interaction System Response Maximum Time | User interaction must generate system acknowledgement in less than 2 seconds. | User will interact with system and the time to system acknowledgement will be timed. | Untested | Brandon Cenci
3.2.1.10 | Electrical and Operation Data Read/Write in Database | Data about electrical performance and system operation must be read and written in database. | Ability to read and write sample data into database will be tested to verify the database can hold the necessary information. Will be used in integration. | Untested | Brandon Cenci
3.2.1.11 | Data Read/Write Maximum Latency | Data about system performance and operation must be able to be read/written in under 2 seconds per entry. | The time average of several entries written/read to/from the database will be measured to determined average write/read time. | Untested | Brandon Cenci
3.2.2.1 | Mass | The system shall be no more than 10 kg. | Individual parts will be weighed and summed using a scale. | Untested | All
3.2.2.2 | System Area | The system shall fit in an area of 30 in. by 15 in. | The total area of the system wilil be measured using a ruler. | Untested | All
3.2.3.1.1 | Peak Power Consumption | The system shall draw no more than 25W. | The voltage and current draw will be measured using a multimeter. | Untested | All